## Sheet1
Bug ID | Bug Title | Severity | Priority | Reported By | Reported On | Status | Assigned To | Environment | Description | Steps to Reproduce | Expected Result | Actual Result | Additional Information
BUG-001 | Application Crashes When Adding More Than 99 Items of the Same Product to Cart | Critical | High | QA Tester | 2025-04-22 | Open | Development Team | iOS 18.2, iPhone 15 Pro | Application crashes immediately when user attempts to add more than 99 units of the same product to the shopping cart. | 1. Login to application 2. Navigate to any product detail page 3. Set quantity to 99 4. Add to cart successfully 5. Navigate back to same product 6. Add 1 more unit to cart | Application should either add the additional item or display a maximum quantity message | Application crashes immediately with no error message | Crash occurs consistently on multiple devices running iOS 18.0 and later. Android devices show similar behavior but display "Application not responding" dialog instead of crashing.
BUG-002 | Payment Processing Timeout Results in Double Charge | Critical | High | QA Tester | 2025-04-22 | Open | Development Team | All platforms | When payment processing takes longer than 30 seconds, the application shows a timeout error to the user. However, the payment is actually processed on the backend, and if the user retries, they are charged twice for the same order. | 1. Login to application 2. Add items to cart 3. Proceed to checkout 4. Enter valid payment details 5. Place order during high traffic period (or simulate network delay) 6. Wait for timeout error 7. Retry payment | Application should verify if previous payment was processed before initiating a new charge | User is charged twice, but only one order is created in the system | This issue has been verified with multiple payment methods including credit cards and PayPal. The duplicate charge appears in the payment gateway's transaction history but only one order confirmation is sent to the user.
BUG-003 | User Session Not Invalidated After Password Change | Critical | High | QA Tester | 2025-04-22 | Open | Development Team | All platforms | When a user changes their password, existing sessions on other devices remain active. This creates a security vulnerability as anyone with access to a previously authenticated device can continue to access the account even after password change. | 1. Login to application on Device A 2. Login to application on Device B 3. On Device A, navigate to account settings 4. Change password 5. Attempt to use application on Device B without re-authenticating | Device B should require re-authentication with the new password | Device B maintains full access to the account | This issue affects all user types and all platforms. The session token is not revoked or flagged as requiring re-validation after critical account changes.
BUG-004 | Search Results Show Out-of-Stock Items with No Indication | Critical | High | QA Tester | 2025-04-22 | Open | Development Team | All platforms | Search results display out-of-stock items with no visual indication of their inventory status. Users can add these items to cart, but the order fails at checkout with a generic error. | 1. Login to application 2. Search for a product known to be out of stock in the inventory system 3. Observe search results 4. Add item to cart 5. Proceed to checkout | Out-of-stock items should either be filtered from results, marked clearly as unavailable, or prevent addition to cart | Out-of-stock items appear normal in search results, can be added to cart, but cause order failure at final checkout step | This issue is particularly problematic as it wastes user time proceeding through the entire checkout flow only to fail at the final step. The error message displayed ("Unable to process order") does not clearly indicate the inventory issue.
BUG-005 | Push Notifications Not Delivered on iOS After App Background for more than 1 Hour | Critical | High | QA Tester | 2025-04-22 | Open | Mobile Development Team | iOS 18.2, All iPhone models | Order confirmation push notifications are not delivered to iOS devices if the application has been in the background for more than one hour. This results in users not being notified about their order status. | 1. Login to application on iOS device 2. Grant notification permissions 3. Send application to background (home button/swipe up) 4. Wait for more than 1 hour 5. Place an order through another channel (web or another device) 6. Check for push notifications on original iOS device | Push notification for order confirmation should be delivered regardless of how long the app has been in background | No push notification is delivered if app has been in background for >1 hour | Analysis suggests the iOS app may be incorrectly managing background refresh tokens or APNS registration. The issue does not occur on Android devices. If the user manually opens the app, subsequent notifications are delivered correctly until the app is backgrounded again for >1 hour.